## Sheet2
| Estimated hours | Worked hours
Cleanup | 5 | 0
Testing | 40 | 41
PacmanGame | 1 | 0
L3 report | 5 | 2
Animation | 4 | 1
Eatable | 4 | 0
View::Pacman | 4 | 2.5
View::Ghost | 4 | 2
Camera controllers | 1 | 3
Scene | 2
Sprite font | 4 | 2
Table | 1 | 0
Menu | 1 | 0
Sprite | 4 | 9.5
Game screen | 5.5 | 2
Particle system | 3 | 2.5
Sound3D | 2 | 0
R7 report | 2 | 3
Resources | 0 | 0.5
Create map file | 0 | 1.5
ModelObj | 0 | 6
LevelHandler | 0 | 1
Environment | 0 | 2
Line counter | 0 | 1.5

## Sheet3
| LOC | SLOC
R5 | 4303 | 2552
R6 | 5575 | 3356
R7 | 7404 | 4037

## Sheet4
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
Fredrik | 5 | 3.5 | 7 | 16.5 | 12 | 12 | 19
Kim | 7.5 | 3.5 | 4 | 21 | 14 | 16 | 12
Lars | 5 | 4 | 13 | 13.5 | 27 | 12 | 23
Martin | 6 | 4.5 | 7.5 | 14.75 | 9.5 | 11 | 18
Thomas | 5 | 3.5 | 10 | 11 | 20 | 16 | 18

## Sheet5
Worked Hours | Estimated Hours | Subject |  | Worked / Estimated Quotient
2 | 10 | 3D Modelling |  | 0.2
2 | 2 | AI state machine |  | 1
4.5 | 5 | Ai Targeting |  | 0.9
14 | 8 | Animation |  | 1.75
12 | 10 | Architecture overview diagram |  | 1.2
6 | 1 | Camera class |  | 6
7 | 5 | Camera controllers |  | 1.4
9.5 | 10 | Class diagrams |  | 0.95
7.5 | 1 | Cleanup |  | 7.5
1.5 | NULL | Create Map file |  | 1.5
5 | 1 | D3DContext class |  | 5
0.5 | 0.5 | DebugFont Class |  | 1
5 | 8 | Enemy class |  | 0.625
8 | 4 | Environment class |  | 2
2.5 | 1 | Fruit class |  | 2.5
0.5 | 1 | Game class |  | 0.5
3.5 | 7 | Game screen class |  | 0.5
23.25 | 15 | GameplayHandler Class |  | 1.55
3 | 10 | L1 report |  | 0.3
24 | 20 | L2 report |  | 1.2
2 | 5 | L3 prototype |  | 0.4
10 | 4 | Level class |  | 2.5
3.5 | 3 | LevelHandler class |  | 1.1667
3.5 | 2 | Line counting script |  | 1.75
2 | NULL | Meetings |  | 2
2.5 | 1 | Menu class |  | 2.5
8 | 8 | ModelObj class |  | 1
1 | 2 | PacmanGame Class |  | 0.5
20 | 20 | Particle system |  | 1
4 | 8 | Pathfinding |  | 0.5
4 | 8 | Player class |  | 0.5
1 | 1 | Primitives |  | 1
1 | 2 | Putting the Foundation together |  | 0.5
2 | 5 | R1 report |  | 0.4
1 | 1 | R2 report |  | 1
2 | 1 | R3 report |  | 2
6 | 2 | R5 report |  | 3
4 | 2 | R6 report |  | 2
2 | 2 | R7 report |  | 1
3 | 5 | Resource Manager |  | 0.6
0.5 | 1 | Resources |  | 0.5
6 | 8 | Scene class |  | 0.75
18.5 | 18 | Setup Redmine |  | 1.0278
15.5 | 5 | Sprite class |  | 3.1
2 | 4 | SpriteFont |  | 0.5
2 | 2 | State diagrams |  | 1
2 | 3 | Table class |  | 0.66667
41 | 25 | Testing |  | 1.64
2 | 4 | View::Ghost |  | 0.5
2.5 | 4 | View::Pacman |  | 0.625
4 | NULL | WBS |  | 4
2 | 1 | Window class |  | 2
321.75 | 276.5
|  |  | Max | 7.5
Avg | 1.1637 |  | Min | 0.2
|  |  | Avg | 1.5231
|  |  | Median | 1