## Sheet1
Task | Hours
R6 report | 2
GameplayHandler class | 5
Sound3D class | 2
Particle system | 5
Screen class | 7
Sprite class | 5
Menu class | 1
Table class | 3
SpriteFont class | 4
Ground class | 4
Camera controllers | 5
View::Ghost class | 4
View::Pacman class | 4
Pathfinding | 4
View::Eatable class | 4
Animation | 8
Model::Enemy class | 8
Testing | 25
100

## Sheet2
| Estimated hours | Worked hours
L2 | 4 | 24
Debug camera class | 1 | 4
Particle system | 4 | 0
Screens | 2 | 0
HUD elements | 8 | 0
AI state machine | 2 | 1
Pathfinding | 2 | 5
GameplayHandler class | 8 | 3
Scene | 10 | 8
AI class | 0 | 4
ModelObj class | 0 | 4
Research | 0 | 4
R5 | 2 | 2
Lines of code script | 2 | 2
Redmine setup | 0 | 9
Cleanup | 0 | 1

## Sheet3
| LOC | SLOC
Week 17 | 4303 | 2552