## Time_Overview
Pacman

R1: Weekly Report (2 april 8:00)
L1: High Design (5 april 8:00)
R2: Weekly Report (9 april 8:00)
R3: Weekly Report (16 april 8:00)
R4: Weekly Report (23 april 8:00)
L2: Detailed Design (27 april 8:00)
R5: Weekly Report (30 april 8:00)
R6: Weekly Report (7 maj 8:00)
R7: Weekly Report (14 maj 8:00)
L3: Prototype (14 maj 8:00)
R8: Weekly Report (21 maj 8:00)
L4: Final Report (25 maj 8:00)

## WorkDone
Work done current week
Hours
Name	Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8
Fredrik	5	3,5	7	16,5	12	0	0	0
Kim	7,5	3,5	4	21	14	0	0	0
Lars	5	4	13	13,5	27	0	0	0
Martin	6	4,5	7,5	14,75	9,5	0	0	0
Thomas	5	3,5	10	11	20	0	0	0

## TasksDone
Tasks done and completed					OBS! / När ni vill infoga en ny rad (genom att markera en rad, högerklicka och välja Infoga), välj då inte raden precis under rubriken (L1, L2, L3 och L4). Det gör att formlerna uppdaterar sig fel och första raden kommer då inte att räknas med. Det är på grund av detta som jag har lagt in två tomma rader mellan varje rubrik. / Dvs, för att infoga en rad, markera raden två rader (eller mer) under rubriken, ex. rad 5 för att infoga under L1, och välj sedan infoga. / Exempel på hur grafen kan se ut ser ni nedan:
			Clock time		Work Time
Delivery	Task	Task Done	Estimated Hours	Hours spent	Estimated Hours	Hours spent	Number of Tasks	Tasks done
L1: High design	Total		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
	Set up templates	1	2	1,5	10	7,5
	WBS	1	0,5	0,5	2,5	2,5
	Meetings		3	1,8	15	9
	Architecture diagrams		2	1	10	5
	Weekly Reports		1	0,5	5	2
	High Design Report		2	2	10	10

L2: Detailed Design	Total		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
	Class diagrams		6		30
	Architecture		10		50
	Package diagram		1		5
	State Machine diagram		2		10
	Meetings		4,5		22,5
	Weekly reports		3		3
	Report		4		20
	Prototype		160		160

L3: Prototype	Total		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
	State Machine Diagram		1		5
	Meetings		4,5		22,5
	Weekly reports		3		3
	Report		4		20
	Prototype		250		250

L4: Final Report	Total		#NAME?	#NAME?	#NAME?	#NAME?	#NAME?	#NAME?
	Meetings		1,5		7,5
	Weekly Report		1		1
	Report		10		50
	Buffert		42		42

## Tasks
		Clock Time			Total Time (Summed Clock Time for everyone involved)
Week	Task	Estimated Week-Specific Hours	Hours Spent	Estimated Total Hours	Estimated Week-Specific Hours	Hours Spent	Estimated Total Hours	Task Finished
Week 13
	L1							1
Week 14
	L1							1
	Weekly Report	1	0,5
Week 15
	WBS	0,5	2	0,5				1
	Architecture Diagram	10	3	10				1
	Class Diagrams	6	2	6				1
	State Diagrams	2	1	2				1
	Package Diagram	1	0,5	1				1
	Window Class	1	1	1				1
	Particle System	2	2	7
	D3DContext Class	1	1	1				1
	Game Class	1	0,5	1				1
	Weekly Report	2	2,5	1				1
Week 16
	L2 Report	10	0	23				0	Alla
	Class Diagrams	5	9	5				0	Alla
	Render Batch	6	0	6				0	Lars-Kim
	Camera Class	1	1	1				0	Lars-Kim
	Audio Manager	4	4	2				0	Lars-Kim
	Level Class	4	11,75	4				0	Fredrik-Thomas
	Player Class	6	3	6				0	Fredrik-Kim
	Food Class	2	2,5	2				0	Fredrik-Kim
	Game Class	4	2	4				0	Lars-Thomas
	Game Screen States	2	0,5	2				0	Lars-Thomas
	HUD Elements	2	1	2				0	Lars-Thomas
	GUI Elements	4	6,5	4				0	Lars-Thomas
	Resource Manager	5	6	10				0	Lars-Kim
	Game Logic Class	10	12	30				0	Fredrik-Martin
	Enemy Class	15	1,5	30				0	Fredrik-Martin
	Weekly Report	1	4	1		3		0	Kim
	Redmine Setup		5,5
	Object Loader		4
	Other		5
Week 17
	Scene	10			30			0	Kim, Lars, Martin
	Game Logic Class	7,5			15			0	Fredrik, Thomas
	Pathfinding	2			4			0	Kim, Fredrik
	AI State Machine	1,5			3			0	Fredrik, Thomas
	HUD Elements	7,5			15			0	Lars, Thomas
	Screens	1,5			3			0	Lars, Thomas
	Particle System	4			8			0	Martin, Lars
	Debug Camera	1			1			0	Lars
	L2 Report	4,2			21			0	Alla
Week 18
	L2 Report	3	0	23				0
	L3 Prototype Demo							0
	Game Logic Class	10		30				0
	AI Targeting							0
	VFX Shadows							0
	VFX Reflections							0
	VFX Environment Mapping							0
	Camera Controller							0
	Morph Animation							0
Week 19
	L3 Prototype Demo							0
Week 20
	L3 Prototype Demo							0
	L4 Report							0
Week 21
	L4 Report							0