## Time Overview
Pacman
R1: Weekly Report (2 april 8:00)
L1: High Design (5 april 8:00)
R2: Weekly Report (9 april 8:00)
R3: Weekly Report (16 april 8:00)
R4: Weekly Report (23 april 8:00)
L2: Detailed Design (27 april 8:00)
R5: Weekly Report (30 april 8:00)
R6: Weekly Report (7 maj 8:00)
R7: Weekly Report (14 maj 8:00)
L3: Prototype (14 maj 8:00)
R8: Weekly Report (21 maj 8:00)
L4: Final Report (25 maj 8:00)

## WorkDone
Work done current week
Hours
Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Fredrik | 5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
Kim | 7.5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
Lars | 5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0
Martin | 6 | 1.3 | 0 | 0 | 0 | 0 | 0 | 0
Thomas | 5 | 0.3 | 0 | 0 | 0 | 0 | 0 | 0

## TasksDone
Tasks done and completed
Delivery | Task | Task Done | Estimated Hours | Hours spent | Number of Tasks | Tasks done
L1: High design | Total |  | #REF! | #REF! | 1 | 1
| Set up templates | 1 | 2 | 1.5
| WBS | 1 | 0.5 | 0.5
| Meetings |  | 3 | 1.5
| Architecture diagrams |  | 2
| Weekly Reports |  | 1 | 0.5
| High Design Report |  | 2
L2: Detailed Design | Total |  | #REF! | #REF! | 1 | 1
L3: Prototype | Total |  | #REF! | #REF! | 1 | 1
L4: Final Report | Total |  | #REF! | #REF! | 1 | 1
OBS!
När ni vill infoga en ny rad (genom att markera en rad, högerklicka och välja Infoga), välj då inte raden precis under rubriken (L1, L2, L3 och L4). Det gör att formlerna uppdaterar sig fel och första raden kommer då inte att räknas med. Det är på grund av detta som jag har lagt in två tomma rader mellan varje rubrik.
Dvs, för att infoga en rad, markera raden två rader (eller mer) under rubriken, ex. rad 5 för att infoga under L1, och välj sedan infoga.
Exempel på hur grafen kan se ut ser ni nedan: