## Sheet1
Task | Hours
3D modelling | 8
R7 report | 2
Sound3D | 2
Particle system | 2.5
Game screen | 5.5
Sprite | 4
Menu | 1
Table | 1
Sprite font | 4
Scene | 2
Camera controllers | 1
View::Ghost | 4
View::Pacman | 4
Eatable | 4
Animation | 4
L3 report | 5
PacmanGame | 1
Testing | 40
Cleanup | 5

## Sheet2
| Estimated hours | Worked hours
R6 report | 2 | 4
GameplayHandler class | 5 | 1
Sound3D class | 2 | 0
Particle system | 5 | 5
Game screen class | 7 | 1
Sprite class | 5 | 3
Menu class | 1 | 0
Table class | 3 | 2
SpriteFont class | 4 | 0
Environment class | 4 | 6
Camera controllers | 5 | 4
View::Ghost class | 4 | 0
View::Pacman class | 4 | 0
Pathfinding | 4 | 3
View::Eatable class | 4 | 0
Animation | 8 | 13
Model::Enemy class | 8 | 2
Testing | 25 | 0
ModelObj class | 0 | 2
3D modelling | 0 | 2
Cleanup | 0 | 4
AI targeting | 0 | 2
Level class | 0 | 3
Setup Redmine | 0 | 3

## Sheet3
| LOC | SLOC
R5 | 4303 | 2552
R6 | 5575 | 3356

## Sheet4
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Fredrik | 5 | 3.5 | 7 | 16.5 | 12 | 12
Kim | 7.5 | 3.5 | 4 | 21 | 14 | 16
Lars | 5 | 4 | 13 | 13.5 | 27 | 12
Martin | 6 | 4.5 | 7.5 | 14.75 | 9.5 | 11
Thomas | 5 | 3.5 | 10 | 11 | 20 | 16