## Time_Overview
Pacman

R1: Weekly Report (2 april 8:00)
L1: High Design (5 april 8:00)
R2: Weekly Report (9 april 8:00)
R3: Weekly Report (16 april 8:00)
R4: Weekly Report (23 april 8:00)
L2: Detailed Design (27 april 8:00)
R5: Weekly Report (30 april 8:00)
R6: Weekly Report (7 maj 8:00)
R7: Weekly Report (14 maj 8:00)
L3: Prototype (14 maj 8:00)
R8: Weekly Report (21 maj 8:00)
L4: Final Report (25 maj 8:00)

## WorkDone
Work done current week
Hours
Name	Week 1	Week 2	Week 3	Week 4	Week 5	Week 6	Week 7	Week 8
Fredrik	5	0.3	0	0	0	0	0	0
Kim	7.5	0.3	0	0	0	0	0	0
Lars	5	0.3	0	0	0	0	0	0
Martin	6	1.3	0	0	0	0	0	0
Thomas	5	0.3	0	0	0	0	0	0

## TasksDone
Tasks done and completed					OBS! / När ni vill infoga en ny rad (genom att markera en rad, högerklicka och välja Infoga), välj då inte raden precis under rubriken (L1, L2, L3 och L4). Det gör att formlerna uppdaterar sig fel och första raden kommer då inte att räknas med. Det är på grund av detta som jag har lagt in två tomma rader mellan varje rubrik. / Dvs, för att infoga en rad, markera raden två rader (eller mer) under rubriken, ex. rad 5 för att infoga under L1, och välj sedan infoga. / Exempel på hur grafen kan se ut ser ni nedan:
			Clock time		Work Time
Delivery	Task	Task Done	Estimated Hours	Hours spent	Estimated Hours	Hours spent	Number of Tasks	Tasks done
L1: High design	Total		10.5	5.3	52.5	26	6	2
	Set up templates	1	2	1.5	10	7.5
	WBS	1	0.5	0.5	2.5	2.5
	Meetings		3	1.8	15	9
	Architecture diagrams		2	1	10	5
	Weekly Reports		1	0.5	5	2
	High Design Report		2		10

L2: Detailed Design	Total		190.5	0	300.5	0	8	0
	Class diagrams		6		30
	Architecture		10		50
	Package diagram		1		5
	State Machine diagram		2		10
	Meetings		4.5		22.5
	Weekly reports		3		3
	Report		4		20
	Prototype		160		160

L3: Prototype	Total		262.5	0	300.5	0	5	0
	State Machine Diagram		1		5
	Meetings		4.5		22.5
	Weekly reports		3		3
	Report		4		20
	Prototype		250		250

L4: Final Report	Total		54.5	0	100.5	0	4	0
	Meetings		1.5		7.5
	Weekly Report		1		1
	Report		10		50
	Buffert		42		42