## Sheet2
| Estimated hours | Worked hours
Cleanup | 5 | 0
Testing | 40 | 39
PacmanGame | 1 | 0
L3 report | 5
Animation | 4 | 1
Eatable | 4 | 0
View::Pacman | 4 | 2.5
View::Ghost | 4 | 2
Camera controllers | 1 | 3
Scene | 2
Sprite font | 4 | 2
Table | 1 | 0
Menu | 1 | 0
Sprite | 4 | 9.5
Game screen | 5.5 | 2
Particle system | 3 | 2.5
Sound3D | 2 | 0
R7 report | 2 | 2
Resources | 0 | 0.5
Create map file | 0 | 1.5
ModelObj | 0 | 6
LevelHandler | 0 | 1
Environment | 0 | 2
Line counter | 0 | 1.5

## Sheet3
| LOC | SLOC
R5 | 4303 | 2552
R6 | 5575 | 3356
R7 | 7271 | 3886

## Sheet4
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
Fredrik | 5 | 3.5 | 7 | 16.5 | 12 | 12 | 19
Kim | 7.5 | 3.5 | 4 | 21 | 14 | 16 | 0
Lars | 5 | 4 | 13 | 13.5 | 27 | 12 | 23
Martin | 6 | 4.5 | 7.5 | 14.75 | 9.5 | 11 | 18
Thomas | 5 | 3.5 | 10 | 11 | 20 | 16 | 18